SAFARI CONNECT

SPECIFIC ACTIONS & CHECKLIST

Starting: This Week | Review: Every 2 Weeks

🔴 WEEK 1 (IMMEDIATE)

ACTION 1: Implement Cancellation Fee

What to do:

Charge 10% cancellation fee on all cancellations

Send SMS reminder 24 hours before departure

Charge full fare for no-shows

Owner: [Team Lead Name]

Tools needed: SMS service, payment system update

Expected Result: Recover KES 30-40K per month

ACTION 2: Launch SMS Reminder System

What to do:

Set up automated SMS 24 hours before trip

Message: '[Driver name] arriving at [time]. Confirm or cancel.'

Track confirmation rate

Owner: [Tech Lead]

Cost: Low (SMS cost ~KES 1-2 per message)

Expected Result: Reduce no-shows by 20%

✓ DEADLINE: End of Week 1

🟡 WEEK 2 (SHORT-TERM)

ACTION 3: Launch Driver Training Program

What to do:

Identify drivers with rating < 4.0 (need training)

Conduct 2-hour training: customer service, safety, professionalism

Create bonus system: drivers 4.5+ get KES 500/month bonus

Track ratings weekly (not monthly)

Owner: [Operations Manager]

Cost: KES 5,000/month (bonuses + training)

Expected Result: Increase satisfaction from 3.6 to 4.0+ rating

ACTION 4: Scale Friday Operations

What to do:

Add 2-3 extra vehicles on Fridays

Schedule extra drivers for peak times: 6 AM, 9 AM, 5 PM

Test price increase on Friday (+5-10%) — see demand response

Monitor bookings vs capacity

Owner: [Fleet Manager]

Cost: Vehicle rental (~KES 3-5K per day)

Expected Result: +KES 20K revenue per month from Friday

✓ DEADLINE: End of Week 2

🟢 MONTH 1 (MEDIUM-TERM)

ACTION 5: Plan Matatu Fleet Expansion

What to do:

Identify 3 high-demand routes: RT001, RT004, RT002

Research Matatu suppliers & costs

Get quotes for 3-5 new Matatus

Do ROI analysis: break-even timeline

Present business case to leadership

Owner: [Finance Manager]

Cost: Planning only (execution in Month 2-3)

Expected Result: +KES 150K revenue in 6 months (once deployed)

ACTION 6: Launch VIP Loyalty Program

What to do:

Identify top 50 spenders from data

Offer: 10% discount, priority booking, free upgrade

Rewards: Free trip after 10 bookings

Send welcome message + program details

Owner: [Marketing/Customer Success]

Cost: Discounts (~3% of revenue initially)

Expected Result: 90% retention rate (vs 60% normal)

✓ DEADLINE: End of Month 1

📊 TRACK THESE METRICS

Completion rate: Target 95% (from 88%)

Cancellations: Track weekly, aim for <8%

Driver satisfaction: Target 4.5+ average

Passenger satisfaction: Target 3.8+ average

Friday revenue: Measure weekly vs baseline

VIP retention: Track engagement

Overall revenue: Measure monthly

💰 FINANCIAL IMPACT SUMMARY

| Action | Timeline | Expected Gain |
| --- | --- | --- |
| Cancellation penalties | Week 1 | +KES 40K/month |
| Friday staffing | Week 2 | +KES 20K/month |
| Driver training | Week 2 | Better retention |
| Scale Matatus | Month 1-2 | +KES 150K/6mo |
| VIP program | Month 1 | Recurring revenue |

TOTAL POTENTIAL: +KES 210K in 6 months (75% growth)